## Sheet1
Enterprise Support Intelligence System — Sprint Progress Tracker
Project Start Date: |  |  | 2026-06-13
Project End Date: |  |  | 2026-07-03
Sprints | Start Date | TAT (Days) | Task | To-Do | In-Progress | Done
Sprint 1 | 2026-06-12 | 0.5 | task 1 | Project approach document |  | ✓ Done
|  | 0.5 | task 2 | Use case & Success definition |  | ✓ Done
|  | 0.5 | task 3 | Initial System blueprint |  | ✓ Done
|  | 0.5 | task 4 | Evaluation & Measurement Plan |  | ✓ Done
|  | 0.5 | task 5 | Project Setup readiness |  | ✓ Done
Sprint 2 | 2026-06-13 | 0.5 | task 6 | High Level Architecture Diagram |  | ✓ Done
|  | 0.5 | task 7 | ADR: Word document |  | ✓ Done
|  | 0.5 | task 8 | Dashboard Creation using MiroBoard/Trello |  | ✓ Done
Sprint 3 | 2026-06-14 | 0.5 | task 9 | Use case & SLO document submitted |  | ✓ Done
|  | 0.5 | task 10 | Architecture sketch drafted |  | ✓ Done
|  | 1.5 | task 11 | Query categories drafted |  | ✓ Done
|  | 0.5 | task 12 | Evaluation plan |  | ✓ Done
|  | 1 | task 13 | Basic Prompting Structure |  | ✓ Done
|  | 0.5 | task 14 | Fast Api endpoint setup |  | ✓ Done
Sprint 4 | 2026-06-19 | 1 | task 15 | [Database] Golden set ready |  | ✓ Done
|  | 1.5 | task 16 | [Database] Vector DB indexed & Retrieval validated |  | ✓ Done
|  | 1 | task 17 | [Database] SQL schema deployed with scaled data |  | ✓ Done
|  | 0.5 | task 18 | [Backend] MCP or tool integration configured
|  | 0.5 | task 19 | [Backend] Logging and tracing operational |  | ✓ Done
|  | 0.5 | task 20 | [Database] Baseline metrics captured (TSR, latency, Grounded) |  | ✓ Done
|  | 0.5 | task 21 | [Backend] Cost tracking / Observability / Hooks enabled |  | ✓ Done
|  | 1 | task 22 | Memory management(Decision) |  | ✓ Done
| Total | 11 | task 23 | PROTOTYPE 1
Sprint 5 | 2026-06-20 | 1 | task 24 | [Backend] RAG + SQL + Hybrid routing stable |  | ✓ Done
|  | 0.5 | task 25 | [Backend] Tool invocation & Error handling implemented |  | ✓ Done
|  | 1 | task 26 | [Backend] High Risk & Escalation logic working |  | ✓ Done
|  | 0.5 | task 27 | [Backend] Guardrails / Refusal Behaviour validated |  | ✓ Done
|  | 0.5 | task 28 | [Database] Golden set retested & TSR improved |  | ✓ Done
|  | 0.5 | task 29 | [Backend] Latency within target range |  | ✓ Done
|  | 0.5 | task 30 | Known gaps logged for Prototype 1 |  | ✓ Done
Sprint 6 | 2026-06-21 | 1 | task 31 | [Backend] Multi-step reasoning operational |  | ✓ Done
|  | 0.5 | task 32 | [Backend] Dynamic tool selection stable |  | ✓ Done
|  | 1 | task 33 | [Backend] Multi-agent / Role orchestration working |  | ✓ Done
|  | 1 | task 34 | [Database] Hybrid (RAG + SQL) reasoning consistent |  | ✓ Done
|  | 1 | task 35 | [Backend] Escalation & Guardrails validated |  | ✓ Done
| Total | 9 | task 36 | PROTOTYPE 2
Sprint 7 | 2026-06-26 | 0.5 | task 37 | [Database] Complex golden queries passing |  | ✓ Done
|  | 0.5 | task 38 | [Database] TSR improved over Prototype 2 |  | ✓ Done
|  | 0.5 | task 39 | [Backend] SLOs met (TSR + P95 latency) under load |  | ✓ Done
|  | 0.5 | task 40 | [Backend] Security controls validated (RBAC + Guardrails) |  | ✓ Done
|  | 0.5 | task 41 | [Backend] Observability active (Logs, Traces, Metrics,Evaluation) |  | ✓ Done
Sprint 8 | 2026-06-27 | 0.5 | task 42 | [Backend] Cost tracking & budget limits enforced
|  | 0.5 | task 43 | [Backend] Load testing completed & stable |  | ✓ Done
|  | 0.5 | task 44 | [Backend] No critical production risks open |  | ✓ Done
Sprint 9 | 2026-06-28 | 1 | task 45 | [Frontend] Frontend connected to agent backend |  | ✓ Done
|  | 0.5 | task 46 | [Frontend] Auth & session management implemented |  | ✓ Done
|  | 0.5 | task 47 | [Frontend] Role-based access control enforced |  | ✓ Done
|  | 0.5 | task 48 | [Frontend] End-to-end query flow working via UI |  | ✓ Done
| Total | 6 | task 49 | PROTOTYPE 3
Sprint 10 | 2026-07-03 | 1 | task 50 | End to End integration Testing |  | ✓ Done
|  | 0.5 | task 51 | [Frontend] Citations & routing info displayed |  | ✓ Done
|  | 0.5 | task 52 | [Frontend] Escalation / Restricted actions protected |  | ✓ Done
|  | 0.5 | task 53 | Performance and scalability
|  | 0.5 | task 54 | DEPLOYMENT
|  | 0.5 | task 55 | SLO EVALUATION |  | ✓ Done
TOTALS |  |  |  | 53 | 2 | 8
Colour Legend
[Backend] | Agent logic, APIs, tools, routing, guardrails, observability
[Database] | Vector DB, SQL schema, golden sets, retrieval, metrics
[Frontend] | UI, auth, RBAC, end-to-end flows, citations display
[General] | Planning, documentation, architecture, evaluation
Note on G26: shubh: memory management uses langraph inbuilt checkpointing. MemorySaver saves the full TicketState in RAM after every node, keyed by thread_id.this enables multi turn conversation. The graph restored prior state on each new turn. The decsion of production is PostgresSaver which persists to out postgreSQL database so conversation survive server restarts

## Sheet2
S.No | SLO metric | Category | Description | Expected Target | Achieved Value
1 | Faithfulness | Correctness | Correctness of generated answers | >=80%
2 | Answer Relevance | Usefullness | Usefulness of the retrieved chunks and generated output to the query | >=75%
3 | Context Precision | Quality | Quality of retrieved documents — proportion that are relevant | >=70%
4 | Latency | Performance | End-to-end request latency from query submission to response delivery | <=2s
5 | Accuracy | Accuracy | Overall correctness of the system’s answers against ground truth | >=85%
6 | Recall | Completeness | Completeness — proportion of relevant documents successfully retrieved | >=75%
7 | LLM as a judge | LLM Confidence | LLM-as-judge confidence score evaluating overall output quality | >=80%
8 | Task Succes Rate(TSR) | Quality | Measures whether the system produced a correct outcome | >=90%
9 | SQL Correctness | Quality | Measures whether parameterized query results match ground truth on the golden set | >=95%
10 | Source Attribution Rate | Retrieval | the system proves its answer is grounded in retrieved evidence rather than hallucination | 100%
11 | Critical Misclassification Rate | Safety | Measures how often a Critical ticket is not classified as Critical (false negative | <3%
12 | Escalation Recall(Human Handoff) | Safety | 100% recall is the only acceptable target — missing a single mandatory escalation is a system failure, not a statistical outlier. | 100%
13 | Unautorized Data Access(RBAC) | Safety | Any cross-customer data access is a data breach with regulatory and legal consequences | 0 violations
14 | Guardrail effectivness | Safety | Measured against defined attack types | 100%
15 | Query Routing Accuracy | Accuracy | Queries are routed to the correct service or agent. | >=95%
16 | Risk Classification Accuracy | Accuracy | Correctly identifies and classifies risk levels | >=95%